## Sheet1
Fairtrade criteria | Requirement | Specific | Done/needs to be done
MN001 Leadership and strategy | functioning committee…. | Membership includes all those necessary for the delivery of this plan, including all University and Union catering managers; and student reps | Group or sub-groups meet at least every 8 weeks.
| ..that reports into leadership and/or governance structures | Reports to VCE via Environmental Sustainability Steering Group | Submitted March 2024
MN002 Leadership and strategy | SMART action plan | Get Plan endorsed by University Senior Management & Union Board of Trustees via the ESG and Union meetings | Submitted March 2024
|  | Publish Plan | 2024-03-01
MN003 Leadership and strategy | Commitment of intent to support Fairtrade and its values within the last two years signed by senior management and their retail and catering outlets. | Agreed statement re-endorsed by Kath Mitchell (VC University), Vicky Hossack (CEO Union), Chris Meynell, Ibrahim Lorgat, Richard Greensmith & Moz Lynch, | 2023-07-01
MN004 Campaigning & Influencing | Fairtrade Fortnight Activities | Fairtrade Fortnight 2023– see individual sites | Done
MN005 Campaigning & Influencing | Innovative campaigns on Fairtrade, trade justice or ethical consumption, run in partnership with students |  | Done until now (Jan) Leek event and society could be added.
MN006 Procurement, Retail & Catering | All outlets to stock FT products in following categories, & working to increase no of lines OR items sold year on year: Tea, Coffee, Sugar, Hot chocolate/cocoa, chocolate, confectionary or snacks, Cotton clothing | Check that all items are still stocked | Done
MN007 Procurement, Retail & Catering | All commercial outlets stock at least 1 FT line in at least 2 of the following (where category is stocked): soft drinks, wine or beer, Health & Beauty, savoury snacks & nuts, cut flowers, fruit |  | Some issues with supply of bananas, due to lack of demand
MN008 Procurement, Retail & Catering | Point of Sale (POS) material in all relevant outlets | POS material is less than 2 years old, displayed close to products & highlights FT products, with info on benefits of FT to growing communities | Being actioned
MN009 Research and curriculum: | Carry out scoping activities amongst students and/or staff to inform our Fairtrade work,and make the findings publicly available. | Conduct Fairtrade survey of staff & students | Done
MN010 Research and curriculum: | Provide & publicise opportunities for students to investigate Fairtrade, trade justice or ethical consumption issues on or off-campus within their course work or dissertations. |  | Published on website
MN011 Outcomes | Outcomes - Publication of annual progress report, made publicly available | Report written, & published online | Summary of this document will be on the Uni website after approval from ESSG
LD001 | The Union has 1 or more active policies which support FT passed within the last 3 years, & published online. | Blends policy of selling FT as far as possible published online | Done 01/07/2023
LD002 | University has 1 or more active policies supporting FT passed within the last 3 years, and published online. | Fairtrade is included in Environmental Policy add in sustainable food policy | Already in place
LD003 | Within the last two years, the partnership has analysed the inclusion of Fairtrade, trade justice and ethical consumption within other cross-cutting institutional and union plans (e.g. procurement plan, sustainability plan, marketing plan) and made suggestions to the relevant stakeholders of how it could be integrated. |  | Consider for 24/26
LD004 | All internal student group/society purchasing policies, award and funding applications require a commitment to Fairtrade, trade justice and ethical procurement considerations where applicable. If there are preferred clothing suppliers listed for clubs &amp; societies to purchase from, these should all stock Fairtrade-certified cotton as standard. |  | Consider for 24/26
LD005 | There is active leadership on Fairtrade, trade justice and ethical consumption issues from one or more senior members of staff or sabbatical officers in the union and institution. |  | Adam Gomes agreed to be this person
CI001 | FT at inductions | Fairtrade is included in the Welcome Magazine for all new students | Done
CI002 | The partnership has supported one or more student groups to campaign on Fairtrade, ethical consumption or trade justice. |  | Consider for 24/26
CI003 | Within the last two years, the partnership has partnered with a local school or college and worked together on at least one project or campaign over the year. |  | Consider for 24/26
CI004 | Within the last two years, the partnership has partnered with a local off-campus Fairtrade group, and worked together on at least one project or campaign over the year. |  | Consider for 24/26
CI005 | Within the last two years, the partnership has facilitated the creation of a local off-campus or school Fairtrade group, where one doesn't already exist. |  | Consider for 24/26
CI006 | Within the last two years, the partnership has proactively collaborated with another aspiring Fairtrade University or College in achieving Fairtrade status and can demonstrate how their involvement has enabled the attainment of the award. This could include encouraging a previously uninvolved university or college to sign up for the next programme cohort. |  | Consider for 24/26
CI007 | Effective web presence | Update FT web pages every 6 months | Done
CI008 | Social Media |  | Some social media activity - need to be more organised on this in the future
CI009 | Sharing good practice | Peer audit with Kingston University | Done
CI010 | Stall at Freshers’ Fair | Run this year by students. | Done
CI011 | Fairtrade, trade justice and ethical procurement considerations are taken into account in checklists or guidance for events. This should include the requirement of all exhibitors that any relevant giveaways (e.g. cotton tote bags, chocolates, biscuits) are Fairtrade-certified, and that any cotton uniforms are Fairtrade-certified. | Union or Uni? | Consider for 24/26
CI012 | Partnership has supported students to fundraise for Fairtrade Foundation |  | Consider for 24/26
PL001 | The partnership has proactively engaged staff and publicised Fairtrade widely as an option for communal tea, coffee, hot chocolate and sugar in staff areas and offices. | Is this something we could do via the sustainability champions? | The Environment and Sustainability Manager has actioned via the Sustainability champions
PL002 | The partnership's catering providers and licensed premises (internal and/or contracted) offer Fairtrade-certified products as standard in all the following categories (where stocked): Fruit Juice Tea Coffee Sugar Chocolate Wine | Don't think we can achieve this due to lack of Fairtrade Fruit. | Lack of ability to source suitable amount of FT fruit is an issue
PL003 | The partnership has captured FT sales data for the previous two academic years & reported back to the FT Foundation. | FT sales data captured by all 3 procurement partners & reports made to FT Foundation. | Done for Aramark and BLC issue with some from Union as they changed tills mid time period
PL004 | Partnership has included terms in tender documentation that reference Fairtrade requirements for relevant categories, or states that Fairtrade suppliers will be preferred. | Identify tender documentation referring to fairly traded/ethically sourced goods, which is also acceptable & make them available. | Checked with procurement - done
PL005 | There is a procedure and support in place to ensure any new food service tenants or retail/catering outlets provide Fairtrade products wherever possible. |  | Consider for 24/26
PL006 | Either Fairtrade is served as standard in hospitality (e.g. conferences, vacation hotel rooms etc.) across all products which have a Fairtrade option available (tea, coffee, sugar etc.), or within the last two years, demonstrable progress has been made to put this into practice. |  | Awaiting evidence
PL007 | In last 2 years, partnership has engaged with at least 1 of the following stakeholders to adopt or increase FT commitments:a. A relevant purchasing consortium, b. An existing supplier, c. An external brand or retailer |  | Email evidence
PL008 | In the last two years, the partnership has increased the proportion of staff uniforms made from Fairtrade-certified cotton or other materials (where available). |  | Checking
PL009 | The partnership ensures that all promotional T-shirts for events are made from Fairtrade-certified cotton. |  | Ambassador t shirts are ethically sourced
PL010 | Competitions, loyalty cards etc.) are run on FT products periodically throughout the year. |  | Evidenced
PL011 | The partnership can demonstrate an increase in the number of Fairtrade-certified items and/or lines bought for sale in campus commercial outlets over the last two years. |  | No
RC001 | Teaching staff to take part in the Global Goals Teach-In, & include FT issues within their teaching, learning or assessment during annual teach-in week in Feb 2023/24. | This is led by the Responsible Futures Group - Chris Ribchester (Chair) | Responsible futures deliver this
RC002 | Follow-up research amongst broad range of students & staff to inform its FT work, make findings publicly available. Should link back to baseline research conducted as part of the mandatory criteria. |  | Consider for 24/26
RC003 | Support 2 or more students to complete an investigation of FT, trade justice or ethical consumption issues on or off campus within course work or dissertation. Share key findings publicly. |  | Consider for 24/26
RC004 | Peer-review another FT University or College partnership. | Peer audit with Kingston University | Done
RC005 | Baseline curriculum review/audit for FT, trade justice or ethical consumption themes conducted & published | Conducted March 2024 by the Chair | Done
RC006 | Commence or complete research into FT, trade justice or ethical consumption issues, plan to make findings public & utilise for future activities |  | Consider for 24/26
RC007 | At least 1 academic to have joined the FT Directory of Supporting Academics | Deb Raha was the member of this group and left the University in Summer 2023 - but was still within the time constraints for engagement. | Deb Raha was a member in the interviening time perion
RC008 | Partnership has connected its FT work with decolonising its curriculum, by providing students with more opportunities to learn through the lens of producers |  | Done
RC009 | Commenced/completed validation of a module specialising in FT, ethical consumption & trade justice |  | Consider for 24/26